## Sheet1
|  |  | Print Media and Traditional Advertising | [6 empty] | Non-Traditional Advertising
Week | Date | Notes | Posters | 1/4 Sheets | Press Releases | Table Tents/Bulletin Board | Week | Date | Notes | Handouts | Tabling | Class Raps | Swag | GLITTERBOMB
-1 | 5/22 | Meeting 12 | EVALUATE EFFECTIVE/NON-EFFECTIVE STRATEGIES!! |  |  |  | -1 | 5/22 | Meeting 12 | EVALUATE EFFECTIVE/NON-EFFECTIVE STRATEGIES!!
0 | 5/15 | Pride Celebration | Refresh, have 100 to hand out | Refresh, have 300 to hand out | Meet reporters, give interviews. | Refresh. BB #1 up! Take down BB #2. | 0 | 5/15 | Pride Celebration | Drag/regular handouts | Week-long tabling | Class raps | Continue T&B handout | Chalk, 1/4 sheets in lockers, books, laptops, bathrooms
1 | 5/8 | Meeting 11 | Refresh | Refresh | Send out PR's, arrange for reporter presence @ events. | Refresh | 1 | 5/8 | Meeting 11 | Drag/regular handouts | Tabling (1+ days) | Class raps | Continue T&B handout | Chalk, 1/4 sheets in lockers, books, laptops, bathrooms
2 | 5/1 | Meeting 10 | Post at OSU, Corvallis | Post at OSU, Corvallis | Send out PR 3, individual PR's. | Refresh/Post. Bulletin Board #2 up! | 2 | 5/1 | Meeting 10 | Drag/regular handouts | Tabling (1+ days) | Class raps | Begin T&B handout | 1/4 sheets in lockers, books, laptops, bathrooms
3 | 4/24 | Meeting 9 | 65 to SI Poster Project, 150 to UHDS, 200 for general use | 400 to hand out | Draft of PR 3, individual PR's. | Set-up at MU, UHDS | 3 | 4/24 | Meeting 9 | Determine location/frequency of handouts | Tabling (1+ days) | Class raps | Continue taking orders | Email facebook groups, continue being 'concerned'
4 | 4/17 | Meeting 8 | Send weeklong, individuals to HP | Send to HP | Submit to Baro, GT, JO calendars. Continue PR 3 work. | Send to HP | 4 | 4/17 | Meeting 8 | Observe campus / create list of popular places & times | Create volunteer schedule | Ask permission from professors / create class rap schedule | Estimate # needed and order T&B | Email 'concerns'
5 | 4/10 | Meeting 7 | Revisions |  | PR 2 sent out. Begin work on PR 3, individual PR's. | Create format to meet design specs | 5 | 4/10 | Meeting 7 | Observe campus / create list of popular places & times | Reserve tables / identify volunteers for table staffing | Continue creating list / ask permission from professors | Pre-Order T&B forms for Pride Comm
6 | 4/3 | Meeting 6 | 4+ drafts ready for Pride Comm |  | Draf of PR 2. | Find design/posting requirements | 6 | 4/3 | Meeting 6 | Observe campus / create list of popular places & times |  | Create list of classes to rap | T-shirt and bandana design drafts, determine sponsor
7 | 3/27 | Break | Drafts to Advert Subcomm |  |  |  | 7 | 3/27 | Break
8 | 3/20 | Finals |  |  |  |  | 8 | 3/20 | Finals
9 | 3/13 | Dead Week / Meeting 5 | Final drafts to advert committee |  | Continue work on PR 2. |  | 9 | 3/13 | Dead Week / Meeting 5 |  |  |  |  | Form facebook group, gay.com name
10 | 3/6 | Meeting 4 | Continue making drafts |  | Send out PR 1. Begin brainstorm for PR 2. |  | 10 | 3/6 | Meeting 4
11 | 2/27 | Meeting 3 | Use final theme to begin drafts |  | Draft of PR 1 |  | 11 | 2/27 | Meeting 3
12 | 2/20 | Meeting 2 |  |  | Continue working on PR 1 |  | 12 | 2/20 | Meeting 2
13 | 2/13 | Meeting 1 | Sign-up for poster drafting |  | Begin work on PR 1 |  | 13 | 2/13 | Meeting 1