## Sheet1
Pride 2006 Overall Timeline
Week | Date | Notes | Locations | Volunteers | Content | Presenters & Guests | Financial
-1 | 5/22 | Meeting 12 | Communicate problems, evaluate effectiveness of location | Thank you! | Thank yous! Look at evaluations | Thank You! Confirm payments. | Look over actual budget
0 | 5/15 | Pride Celebration | Get to venue >30 min prior, pick up room key, setup room | Coordinate Volunteers | Pass out evaluations | Greet speaker, introduce, be hospitable
1 | 5/8 | Meeting 11 | Final room and equipment check with facilities. | Confirm dates/times with volunteers | Final draft of handouts /materials | Check in w/ presenters | Emergency $ needs due. Purchase food, materials.
2 | 5/1 | Meeting 10 |  | Continue signing-up and recruiting. | Final draft of program |  | Communicate specific material needs.
3 | 4/24 | Meeting 9 | Finalize equipment needs. | Begin signing up volunteers. Continue recruitment. | First draft of handouts /materials | Finish Service Contracts get press information | Create purchase requests.
4 | 4/17 | Meeting 8 | Final equipment needs. Facilities meeting. | Final volunteer needs to Co-Chairs. | Submit Event Description. | Start Service Contracts. Get equip. needs/ contract info | Talk with Name, confirm all co-sponsors and grants.
5 | 4/10 | Meeting 7 | Continue working on equipment needs. | Confirm volunteer needs. Continue recruitment. | Check-in with subcommittees. | Confirm Presenters. | Confirm all $ needs to Co-Chairs
6 | 4/3 | Meeting 6 | Finalize location, time, day. Draft of equipment needs due. | Confirm volunteer needs. Start recruiting! | Check-in with subcommittees. | Decide presenters/speakers.
7 | 3/27 | Break |  | Brainstorm volunteer needs. | Check-in with subcommittees. | Decide presenters/speakers
8 | 3/20 | Finals |  | Brainstorm volunteer needs. | Check-in with subcommittees. | Continue discussion of speakers/presenters.
9 | 3/13 | Dead Week / Meeting 5 | Reserve other rooms if needed. | Brainstorm volunteer needs. | Check-in with subcommittees. Final event commitments. | Continue discussion of speakers/presenters.
10 | 3/6 | Meeting 4 | Reserve other rooms if needed. | Brainstorm volunteer needs. | Confirm theme. Confirm event subcommittees. | Begin discussion of speakers/presenters. | Grants and cosponsorships finalized.
11 | 2/27 | Meeting 3 | Reserve other rooms if needed. | Continue creating volunteer program. | Final list of themes. Begin event subcommittees. |  | Discuss cosponsorship and grants.
12 | 2/20 | Meeting 2 | Reserve other rooms if needed. | Continue creating volunteer program. | Brainstorm theme and events |  | Discuss cosponsorship and grants.
13 | 2/13 | Meeting 1 | Examine current room reservations. Determine other rooms needed. | Begin creating volunteer program. | Brainstorm theme and events. Create advert subcommittee. | Brainstorm possible speaker costs | Discuss budget breakdown, cosponsorship, grants.